## Assignment1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Abdul Hakim Abbas			Date	3/10/2016				1. Enter your name, and the date you started the programming assignment.
Program	Part C			Program #	37				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Paul J Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0			0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0			0
Modified (M)			(counted)	0			0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0			0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	65			65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		0	0		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			25	8	20	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			25	12	20	32	14%
Code			55	35	59	94	42%
Compile			5	3	15	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			12	17	12	29	13%
Postmortem			18	10	14	24	11%
Total			140	85	140	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-		This Assignment dealt with Exercise 37 Part C. And it has been programmed up to solve the problems presented on it.
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				Abbas			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment2
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment3
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment4
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment5
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment6
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment7
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment8
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment9
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment10
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment11
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Final_Project
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	65		65		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					28	28	12%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					32	32	14%
Code					94	94	42%
Compile					18	18	8%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					29	29	13%
Postmortem					24	24	11%
Total			0	0	225	225	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)