## Assignment1
				0. Purpose: This worksheet contains the estimated and actual project data.
Student	Abdul Hakim Abbas			Date	3/24/2016				1. Enter your name, and the date you started the programming assignment.
Program	Assignment 4			Program #	4				2. Include program name in cell B2, and assignment number in cell F2.
Instructor	Paul J Conrad			Language	Java				3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0			0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0			0
Modified (M)			(counted)	0			0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0			0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	50			50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		0	0		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning			50	45	36	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design			45	38	50	88	16%
Code			55	42	135	177	32%
Compile			30	25	33	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test			35	35	47	82	15%
Postmortem			25	25	34	59	11%
Total			240	210	335	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-		This is Assignment #4 dealt with Exponentiation and GCD. And you can use the Euclid's Algorithm to find the gcd.
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				Abbas			By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment2
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment3
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment4
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment5
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment6
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment7
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment8
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment9
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment10
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Assignment11
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)

## Final_Project
				0. Purpose: This worksheet contains the estimated and actual project data.
Student				Date					1. Enter your name, and the date you started the programming assignment.
Program				Program #					2. Include program name in cell B2, and assignment number in cell F2.
Instructor				Language					3. Include your instructor's name in cell B3, and the programming langauge used in cell F3.
				Last (ToDate from previous program)
Program Size (LOC)				Actual			To Date		Prior to development:
Base (B)			(counted)	0	0		0		0. If you are modifying or enhancing an existing program, count the program's LOC and enter it in cell E7; otherwise enter 0.
Deleted (D)			(counted)	0	0		0
Modified (M)			(counted)	0	0		0		1. If you are modifying or enhancing an existing program, put into cell E8 the number of LOC you are deleting from your original program; otherwise enter 0.
Added (A)			(T-B+D-R)	0	0		0
Reused (R)			(counted)	0	0		0		2. If you are modifying or enhancing an existing program, put into cell E9 the number of LOC you are modifying from your original program; otherwise enter 0.
Total New and Changed (N)			(A+M)	0	0		0
Total LOC (T)			(counted)	0	50		50		3. If you are modifying or enhancing an existing program, put into cell E11 the number of LOC you are reusing from your original program; otherwise enter 0.
		LOC/Hr		-	-		0
				Last (ToDate from previous program)				After development:
Time in Phase (minutes)			Plan	Actual		To Date	To Date %		4. Measure your finished program total LOC, and enter the value into cell E13.
Planning					81	81	15%		5. Record data from your previous program into the respective cells under the Last Program column. This should automate the ToDate columns.
Design					88	88	16%
Code					177	177	32%
Compile					58	58	11%		Time in Phase: Under the Plan column, enter the number of minutes you plan will take for each phase (planning, design, code, etc). In the Actual column, enter the actual time it took for each phase. In the To Date column, enter the total of your actual time for the phase and the To Date time of your most recent project you have completed.
Test					82	82	15%
Postmortem					59	59	11%
Total			0	0	545	545	100%
				Last (ToDate from previous program)
Defects Injected				Actual		To Date	To Date %		Defects Injected/Removed: In the Actual column, enter the actual number of defects found for each phase. In the To Date column, enter the total of your actual number of defects found for the phase and the To Date number of defects found in your most recent project you have completed.
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-		Summary
Postmortem					0	0	-
Total Development				0	0	0	0%
				Last (ToDate from previous program)
Defects Removed				Actual		To Date	To Date %
Planning					0	0	-
Design					0	0	-
Code					0	0	-
Compile					0	0	-
Test					0	0	-
Postmortem					0	0	-
Total Development				0	0	0	0%
After Development				0	0	0

				By typing in your name in the box to the left of this notice, you are certifying that this document has been reported accurately; and any misinformation can be treated as Academic Dishonesty.
				(eSignature)